## Sheet1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
Virtual Machine goes down for the application | Application will go offline and be unable for user | Low | High | Amazon Web Services | Need to recreate the infrastructure again on another machine | Use infrastructure as code to recreate machines quickly
When app is deployed there is an issue with it. | The application will have issues and will not function as normal. | Medium | High | Group Members | Rollback to the most stable up to date version | Automate test before any applications are deployed, if tests do fail, it should not deploy the application
Accidental share of password | The security of the application will be compromised | Low | High | Group Members | Remove and update password | Add the password as an environment variable, this adds additional security as it is not stored in any files
Internet Connection Problems | Would not be able to connect to and ssh with ec2 instances, also would lose some time working on the project | Low | High | ISP | Focus on the work that can be completed with no internet access | You can use mobile data in the event of the internet going down, also hold regular meeting and discuss plans for the following days. Remaining team members can work together to make up for the missing person.
Group Member off sick | One member will need to do the work for the day | Low | Medium | Group Members | Focus on your own tasks and try to complete the other group members work | Schedule regular meetings to discuss the plan for work, enables you to be aware of the tasks of all group members
Worker node crashes | There will be one less worker node and the remaining worker node will have to work harder, will result in added stress | low | low | Amazon Web Services | Close the instance and rebuild the worker node | Add auto scaling group, in the event one worker node crashes, another will be created automatically
Files are accidentally deleted | The group will have lost the work they have been working on | Low | High | Developer | Rebuild the lost files again | Make sure all files are backed up online or uploaded to the git repository
Behind on work due to poor planning | Will result in the group not completing the project and not meeting the required specification | Low | High | Group Members | Hold an emergency meeting to figure out how they can meet the project spec | Make sure Jira boards are created, this allows proper planning for the project going forward.
The instance for the database goes down | Will result in the application failing as there will be data the front end can request from | Low | High | AWS | Create new RDS and implement the database again to work with the application | Create a second RDS, so that it may be used as a back-up in the event the first one fails.
Running out of resources for an EC2 instance | Will have an effect on the performance of the EC2 as there is little memory/CPU remaining | Low | Quite High | AWS | Upgrade the EC2 instance/ create a new one with increased performance | Use an auto scaling group and set a value it tracks for CPU usage, if it does reach that CPU level, another EC2 instance will be created.